ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	4

2.1.	Overall objective	4

2.2.	Purpose	4

2.3.	Results to be achieved by the Contractor	5

3.	ASSUMPTIONS & RISKS	6

3.1.	Assumptions underlying the project	6

3.2.	Risks	6

4.	SCOPE OF THE WORK	8

4.1.	General	8

4.2.	Specific work	9

4.3.	Project management	16

5.	LOGISTICS AND TIMING	17

5.1.	Location	17

5.2.	Start date & Period of implementation of tasks	17

6.	REQUIREMENTS	17

6.1.	Staff	17

6.2.	Office accommodation	21

6.3.	Facilities to be provided by the Contractor	21

6.4.	Equipment	22

7.	REPORTS	22

7.1.	Reporting requirements	22

7.2.	Submission and approval of reports	22

8.	MONITORING AND EVALUATION	23

8.1.	Definition of indicators	23

8.2.	Special requirements	23

# BACKGROUND INFORMATION

## Partner country

Macedonia

## Contracting Authority

The association “Unikum-kos” as Leading partner (LP) in the project “FEMTERPRISE – Fostering the creation of social enterprises by strengthening the entrepreneurial potential of young women” financed by the Interreg-IPA "Bulgaria – the former Yugoslav Republic of Macedonia" cross-border programme 2014-2020 with Subsidy Contract № РД-02-29-221/17.10.2016

” UNIKUM-KOS” is a civil society organization of woman entrepreneurs Stojanovska that was founded in September 2013. The organization is led by Mrs Sonja Stojanovska in a role of president. The association is established in order to connect the women in the business sector at the local, regional, national and international level in order to develop their own business. The organization aims to provide variety of business opportunities, identifying and using available domestic and foreign resources (partners, knowledge, new markets, capital, technology).

## Country background

According to the EC 2020 Entrepreneurship Action Plan, women constitute 52% of the total European population but only 34.4% of the EU self-employed and 30% of start-up entrepreneurs. As reported by the EC Statistical Data on Women Entrepreneurs in Europe the percentage of female entrepreneurs in the total active labour force (entrepreneurship rate) is 8% in Bulgaria and 10% in FYROM (2012).

Female creativity and entrepreneurial potential are an under-exploited source of economic growth and jobs that should be further developed and promoted among potential investors in the cross-border region of Bulgaria and FYROM. When establishing and running a business, women in both countries face more difficulties than men, mainly in access to finance, training, networking, and in reconciling business and family.

Difficulties faced by Bulgarian and Macedonian female entrepreneurs are often related to lack of access to finance and information, including tools for networking and navigating entrepreneurship’s legal and regulatory framework, deficit of management knowledge and skills and low levels of mentor support. Public support services are not of the necessary quality and do not reach all those in need. There is also a widespread culture that does not celebrate successful (female) entrepreneurs as role models.

## Current situation in the sector

- There is an urgent need to create labour opportunities for women in the border region, incl. stimulating business start-up and self-employment. Social enterprises are important drivers of inclusive job creation and social innovation. They generate sustainable jobs and have demonstrated a stronger resilience to the crisis than the general economy. Social entrepreneurs are innovators, drive social inclusion and contribute to achieving the objectives of the EU2020 strategy.

- Effective support of female entrepreneurs in the BG-FYROM border region consists of applying holistic approach that integrates essential elements like management training, mentor coaching and networking with peers, investors and clients. Potential women entrepreneurs should be made aware of business support programmes and funding opportunities.

- The European Commission promotes and supports female entrepreneurship through the Small Business Act and the Entrepreneurship 2020 Action Plan. Initiatives such as the FEMTERPRISE project, aiming to support networking among female entrepreneurs, potential female entrepreneurs, and support organisations are highly encouraged by the EC.

- Developing and promoting female creativity and entrepreneurial potential is associated with the following EU and national strategies:

            - EC Entrepreneurship Action Plan 2020,

            - A “Small Business Act” for Europe

            - Bulgarian National Youth Strategy 2010-2020;

            - National Strategy to Reduce Poverty and Social Exclusion in the Republic Macedonia 2010 2020;

            - FYROM National Action Plan for SMEs 2016-2020: stimulating self-employment, social entrepreneurship and promotion of entrepreneurship.

## Related programmes and other donor activities

The project fits into and creates synergies with the following EU territorial cooperation strategies:

1. "Europe 2020: “Inclusive growth” – by fostering territorial cooperation for socio-professional advancement of young women thus contributing to the increase of youth employment and decrease of poverty rates.

2. European Territorial Agenda 2020: “Ensuring global competitiveness of the regions based on strong local economies” – by empowering young female entrepreneurs and fostering the creation of social enterprises in the region thus strengthening human capital, capacity for innovation and bringing ideas to the market.

3. EUSDR: Pillar 3 “Building prosperity in the Danube Region”, Priority Area 08 "To support the competitiveness of enterprises""; Priority Area 09 “Investing in People and Skills”

4. Partnership Agreement of the Republic of Bulgaria;

5. EU Country Strategy Paper (2014-2020), FYROM;

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

- The project”FEMTERPRISE” will establish supportive and creative environment for 30 young female entrepreneurs to successfully set-up their own enterprises and to provide innovative, sustainable solutions to social and environmental issues in the border region. The project envisages multiple joint online and offline capacity-building, networking, awareness-raising and promotion interventions for reaching and sustaining its positive impact on at least 3000 representatives of the target groups and ensuring long-lasting business cooperation in the region.

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To improve the conditions for business development in the cross-border area by applying innovative non-formal approach for strengthening the entrepreneurial capacity of female entrepreneurs aged 18-29 and fostering the creation of social enterprises.

The specific objectives of the project are as follows:

1) To establish a sustainable cross-border FEMTERPRISE Network of Women Entrepreneurs;

2) To strengthen the entrepreneurial capacity and to create opportunities for professional and social realization of young female entrepreneurs;

3) To develop an innovative, sustainable and supportive online tool for capacity building, mentoring and networking between female entrepreneurs, mentors, clients and potential investors from the cross-border region;

4) To foster the creation of female –run social enterprises in the region;

5) To promote entrepreneurial culture and social entrepreneurship.

  - Purpose

The association Unikum-kos will make a research, select and contract 2 experts: jurist and business mentor as members of the multidisciplinary FEMTERPRISE mentor team, which will be consisted of 6 experienced and proven professionals.  The other 4 members of the team will be selected and contracted by the Bulgarian project partner (PP2) -Viva Pautalia Association. Although the experts will be hired in a separate procedures by the two project partners, all experts are supposed to work as one team, shall have intensive collaboration and shall establish feedback mechanisms.

The purposes of this contract are as follows:

## To develop the program-methodological content of the FEMTERPRISE platform and the “Create your own business model” tool;

## To develop the content of the Social Entrepreneurship Practical Guide;

## To provide ongoing support and guidance of the project participants and project management team at all stages of project implementation;

## To develop a holistic concept (methodology) for organization and conducting the FEMTRERPRISE capacity-building and empowerment training for young women entrepreneurs and to lecturе and moderatе the training sessions in accordance with the developed concept (methodology);

- To develop a holistic concept (methodology) for organization and conducting the FEMTERPRISE online competition for development of 6 social enterprise concepts and to guide and moderate the competition in accordance with the developed concept (methodology);

- To develop a holistic concept (methodology) for organization and conducting the FEMTERPRISE networking workshop and lecturе and to moderatе the training and workshop sessions in accordance with the developed concept (methodology);

## To provide ongoing mentor guidance and support of the project participants in the real world development of the winning FEMTERPRISE concept for cross-border social enterprise.

## To provide professional advice to the remaining 5 teams for further development of their concepts.

## To actively participate in the promotion campaign by providing professional mentor advice and guidance via the web platform and social media.

## To provide professional consultation to the project management team with regard to eventual upgrade the FEMTERPRISE platform content after the project closure.

# Results to be achieved by the Contractor

# Developed program - methodological content of the FEMTERPRISE platform and “Create your own business model” tool;

# Developed program - methodological content of the Social Entrepreneurship Practical Guide;

# Developed holistic concept for organization and conduction of the FEMTERPRISE  training, workshop and online contest– programme, scenario, training modules, tasks for the teams, feedback forms etc.;

# Real-world developed winning FEMTERPRISE concept for social enterprise;

# On-going mentor advice is provided to project participants.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Direct and final beneficiaries will be interested and willing to participate in the project;

- There will be adequate financial and human resources to implement the project;

- There will be timely verification and reimbursement of expenditure on behalf of FLC. MA and NA

- The tender procedures under the project will be organized without delay;

- The project activities will be implemented in accordance with the project action plan;

- There will be adequate staff available from the selected contractors to implement the assigned tasks in strict accordance with their respective contracts and the Programme rules.

- The project management team and the selected contractors will implement their tasks in close cooperation and coordination;

- The comments and recommendations of direct project participants will be taken into account when designing and developing the FEMTERPRISE platform and the online information and promotion campaign.    														.

## Risks

| Description of risk | Likelihood | Impact | Risk mitigation plan |
| --- | --- | --- | --- |
| Insufficient financial and human resources to implement the project | LOW | MEDIUM | Undertaking all legal and financial actions necessary for the timely and adequate provision of human and financial resources by the project partners in strict compliance with the obligations provided in the Subsidy Contract and Partnership Agreement, as well as with the Programme rules and guidelines. The joint project management team will implement constant monitoring on the financial progress and quality of performance of sub-contractors and will undertake corrective measures if necessary. |
| Direct and final beneficiaries uninterested or unwilling to participate in the project activities | LOW | MEDIUM | Drafting comprehensive and coherent Terms of Reference and procurement contracts in order to ensure adequate methodology design for identification and involvement of FEMTERPRISE NETWORK members, democratic and transparent process of involvement of direct project participants, innovative and engaging awareness-raising and promotion interventions. |
| Non-compliance with the time schedule of project activities due to circumstances of various nature | LOW | MEDIUM | Careful planning and forecasting in the project preparation process. Establishment of regular monitoring and corrective procedures by the joint project management team. |
| Delayed verification and reimbursement of expenditures on behalf of FLC, MA and NA | MEDIUM | LOW | Ensuring additional financial resources necessary for the successful completion of the project. |
| Poor design and development of the FEMTERPRISE platform and its content leading to user-unfriendly and outdated design and inadequate and ineffective content | LOW | MEDIUM | Drafting comprehensive and coherent Terms of Reference and procurement contracts, constant monitoring and reporting on the progress of the activities, project teams, mentors and contractors working in close cooperation and interacting constantly, directly involving project participants in the evaluation of the design of the platform and the quality of its content |
| Poor design and implementation of the online information and promotion campaign leading to failure in reaching and involving project indirect beneficiaries | LOW | MEDIUM | Drafting comprehensive and coherent Terms of Reference and procurement contracts, constant monitoring and reporting on the progress of the activities, project teams, mentors and contractors working in close cooperation and interacting constantly, directly involving project participants in the campaign design |

# SCOPE OF THE WORK

## General

### Description of the assignment

## An important element to change the entrepreneurial culture is thus a change in the perception of entrepreneurs through practical and positive communication about their achievements, their value to society and the opportunities of new social business creation as a career destination. To achieve this, their visibility as role models must be stepped up, taking into account the diversity of entrepreneurial profiles and paths to success. Furthermore, the visibility of successful professionals will show project participants that they have chances of success in their chosen field. For this reason, the project envisages active involvement of mentors as contracted consultants who will form the multidisciplinary FEMTERPRISE mentor team.

## The FEMTERPRISE mentors are substantial founding members of the established under the project FEMTERPRISE Cross-border Network of Women Entrepreneurs. They should act as role models, inspiration and advisors of 30 young women with entrepreneurial potential from the cross-border region of Bulgaria and FYROM.  The professional mentor team should embody the driving force to help those women reach their full potential, successfully set-up their own enterprises and provide innovative, sustainable solutions to social and environmental issues in the cross-border region. They should facilitate the project participants training and professional growth as social entrepreneurs, create a positive counselling relationship and climate for open communication, provide information, guidance and constructive comments, support, encourage and critically assess performance of the project participants in the trainings and assigned tasks.

## In order to provide professional mentor consultancy, the association Unikum-kos aims to contract a company for consultancy services that will propose 2 experts: jurist and business mentor who will represent the Macedonian part of the joint multidisciplinary FEMTERPRISE mentor team. The joint mentor team will be comprised of six experienced and proven professionals with diverse profile from Bulgaria and Macedonia. The Bulgarian part of the mentor team will be comprised of 4 professionals – jurist, business mentor, psychologist and financial & fundraising expert. The Macedonian part of the mentor team will be comprised of 2 professionals – jurist and business mentor. The mentors will be responsible for the development of the program-methodological content of the FEMTERPRISE platform and the “Create your own business plan” tool, the development of the content of the Social Entrepreneurship Practical Guide, development and implementation of a program and methodology concept for organization and conduction of the FEMTRERPRISE capacity-building and empowerment training for young women entrepreneurs, facilitation and moderation of the Training, the following online competition for development of 6 social enterprise concepts and creating the program and methodological concept and facilitation of the networking FEMTERPRISE workshop. As addition the Mentors team will be responsible for providing ongoing mentor consultancy, support and guidance to the participants and project team at all stages of project implementation. They should support and guide project participants in the in the real world development of the winning FEMTERPRISE concept for cross-border social enterprise and should provide professional advice to the remaining 5 teams for further development of their concepts.

### Geographical area to be covered

### The cross border region of Bulgaria Republic and Republic of Macedonia.

### Target groups

Young women with entrepreneurial potential aged 18-29, successful entrepreneurs and social entrepreneurs to act as volunteer mentors, local and regional workforce, local and regional stakeholders, businesspersons, investors, NGOs, policy makers, media.

## Specific work

The contracted company /Contractor/ will be required to perform the following specific tasks:

### Development of the program-methodological content of the FEMTERPRISE platform and the “Create your own business model” tool:

### In collaboration with the Bulgarian members the mentors should develop a comprehensive database of informational, capacity-building and self-assessment materials and tools which will be uploaded at the web platform. The Macedonian members of the team will be in charge on the development of the platform content related to Macedonian legislative provisions and funding opportunities.

The content of the trilingual (MK, BG, ENG) FEMTERPRISE online capacity-building and networking platform with mobile version should consist as minimum the following modules and sub-modules:

FEMTERPRENEURIAL SKILLS: This module should encompass the following sub-modules:

Leadership skills:

This section should encompass the key leadership skills for entrepreneurs and social entrepreneurs. The section should be developed in and attractive and engaging for the participants way. The section should ultimately serve as tool for identification and self-development of the necessary skills to be an effective leader, successful and dedicated (social) entrepreneur.

Entrepreneurship:

This section should present the phenomenon of entrepreneurship from the personal perception and professional experience of a successful entrepreneur/businessperson, and not as a dry textbook term. The Consultant should describe and interpret the motivation, steps, fears, challenges, setbacks on the path of success, highlighting the country and cross-border area specifics, and, of course, sharing the joy and fulfillment of being a successful entrepreneur.

Social entrepreneurship:

Social entrepreneurship is the attempt to draw upon business techniques and private sector approaches to find solutions to social, cultural, or environmental problems. This concept may be applied to a variety of organizations with different sizes, aims, and beliefs. Conventional entrepreneurs typically measure performance in profit, revenues and increases in stock prices, but social entrepreneurs also take into account a positive "return to society". Social entrepreneurship typically attempts to further broad social, cultural, and environmental goals often associated with the voluntary sector. At times, profit also may be a consideration for social enterprises, but not as an end in itself, but rather as a means to further the social or cultural goals of the organization.

Social enterprises combine societal goals with entrepreneurial spirit. These organisations focus on achieving wider social, environmental or community objectives. A social enterprise is an operator in the social economy whose main objective is to have a social impact rather than make a profit for their owners or shareholders. It operates by providing goods and services for the market in an entrepreneurial and innovative fashion and uses its profits primarily to achieve social objectives. It is managed in an open and responsible manner and, in particular, involves employees, consumers and stakeholders affected by its commercial activities. The European Commission aims to create a favorable financial, administrative and legal environment for these enterprises so that they can operate on an equal footing with other types of enterprises in the same sector. The Social Business Initiative launched in 2011 identified actions to make a real difference and improve the situation on the ground for social enterprises.

This section should describe in detail the concept of social entrepreneurship and social enterprises in the cross-border, European and global context, illustrating in an attractive way what are social enterprises, in which fields thy operate, what are the key factors for establishing a successful social enterprise and the key features of a successful social entrepreneur. Successful examples of Bulgarian, Macedonian and other European and/or global social enterprises should be given in the form of short presentations together with links to their respective websites.

The personal approach applied for section “Entrepreneurship” is advisable for this section as well. This section should clearly explain the difference between a social project and a social enterprise!

GO FEMTERPRENEURIAL

This module should provide users with basic knowledge and skills to construct, modify and improve the business model of their enterprise. The module should encompass the following sub-modules:

Identifying Problems & Solutions

The Consultant should provide a Step-by-Step approach for successful and proper identification of the social/ecological problems to be addressed by creating social enterprises as well as for finding viable and sustainable solutions of those problems.

Value proposition

The Consultant should provide a Step-by-Step approach for successful and proper identification of the potential customers’ needs, and how to design products and services customers want.

Business modelling

“Create your own business model” tool – the content of this sub-section should cover all major elements of the business modeling of a start-up company and should represent a practical tool for planning and self-education. It will be used by FEMTERPRISE platform users to build the framework for their new or existing enterprise / social enterprise.

The “Create your own business plan” tool content should meet the following criteria:

•	User-friendly;

•	Represent a Step-by-Step solution to creating a business model;

•	Encompass all essential components of a start-up business model;

Legal:

This sub-section should present, explain and refer to the legal provisions concerning social enterprises in Bulgaria and Macedonia, offering a step-by step approach for identifying the appropriate legal entity form for the users’ social enterprises, as well as for registering the social enterprise as legal entity. This section should also provide basic knowledge on commercial and tax law applicable for social enterprises.

Pitch your social enterprise idea:

The content of this sub-section should cover the approach and major elements of a successful and attractive presentation of an enterprise/social enterprise idea to potential investors.

FEMTERPRISE BUSINESS OPPORTUNITIES:

This section should encompass a presentation of business opportunities for establishing a social business in the cross-border area identified by the research implemented under the project, accompanied by a short analysis from a mentor’s business, legal and fundraising perspective.

FEMTERPRISE NETWORK:

Mentors /Entrepreneurs/Investors area:

This sub-section will comprise of personal profiles of the FEMTERPRISE Network members – professional mentor team, volunteer mentors (will be identified and involved in the research phase and will take part in the online popularization campaign and the FEMTERPRISE networking workshop), the young female entrepreneurs participating in the project and all those interested in creating their profile and benefiting from the platform resources, as well as potential investors interested in the presented social enterprise ideas. The Bulgarian mentor team will be responsible for creating their profiles in the platform and advising the project participants on how to create theirs in order to present themselves to potential investors and peers as social innovators with attractive concepts. The creation of profiles of mentors and participants should take place at the FEMTERPRISE entrepreneurial training.

FEMTERPRISE competition (online phase):

This sub-section will represent the online phase FEMTERPRISE competition. The FEMTERPRISE Competition will be launched at the FEMTERPRISE training and will continue online through the platform and social media, lasting 3 months. Its purpose is to foster creative and competitive environment for generating 6 FEMTERPRISE concepts for cross-border social enterprises.

The 30 young female entrepreneurs will be divided into 6 teams comprising of average 5 members (balanced BG/FYROM participation) and 1 mentor each. In order to maximize the mentor expertise, mentors (including the Macedonian) will rotate on 2-week basis, thus providing the necessary specialized expertise (legal/business, etc.) to each team. Online promotion campaign will run in parallel with the competition and contestants will attract supporters of their ideas, thus popularizing the project and the platform among target groups.

The mentor team will be responsible for guiding the teams of participants into identifying and developing their holistic concept of a cross-border social enterprise, assigning tasks and regular online “meetings” of the teams in order to discuss, moderate and assess the progress of each team’s idea, motivate participants to be proactive and responsible team players, and, in the end, come up with a holistic concept of a cross-border enterprise which will be presented and assessed by an independent cross-border jury at the FEMTERPRISE workshop following the online contest.

Networking area:

This section will represent the networking area between mentors, entrepreneurs and investors. The Consultant is expected to provide input, advice and (if applicable) to facilitate links between entrepreneurs and interested investors throughout the project implementation.

Success stories:

The project envisages each of the developed 6 cross-border social enterprise ideas to be presented in a short video elaborated by the participants during the FEMTERPRISE training and mounted, voiced and subtitled by a professional company. These videos will represent our first FEMTERPRISE success stories (came to life with the professional guidance and advice of the mentor team) and will serve as inspiration for many other new FEMTERPRISE network members to step into the world of social entrepreneurship. Mentors are required to provide their professional opinion on the videos, as well as feedback and advice on how to make them an engaging instrument for attracting both potential FEMTERPRISE entrepreneurs and investors.

The FEMTERPRISE platform will represent the online aspect of the established within the project FEMTERPRISE Network of Women Entrepreneurs, thus allowing many new members to join and make use of its resources free of charge, during and after the project closure. The platform will empower and connect women entrepreneurs by establishing an (online) community that's safe and supportive, and aims to provide mutually beneficial relationships between professional women. The platform should also serve as an awareness-raising and promotion tool, enabling users to create profiles, develop partnerships, exchange and promote their ideas among peers and investors, share knowledge, promote entrepreneurship and foster the creation of women-led enterprises and social enterprises supported and guided by experienced mentors.

### Development of the content of the Social Entrepreneurship Practical Guide:

### The guide should describe in detail the concept of social entrepreneurship and social enterprises in the cross-border, European and global context, illustrating in an attractive way what are social enterprises, in which fields they operate, that are the key factors for establishing a successful social enterprise and the key features of a successful social entrepreneur. The guide should also provide a step-by-step approach for creating a social enterprise, including tools, tips and advice for young people who aspire to create social change by highlighting the realities and opportunities for social enterprise in a cross-border context. It should also contain examples of successful social enterprises. The guide will be available for free download from the FEMTERPRISE platform and will be printed in 300 copies – 150 in Bulgarian and 150 in Macedonian in order to be disseminated among project participants and target groups.

### Providing current support and guidance to the participants and project team at all stages of project implementation.

The Consultant should provide ongoing support and mentor guidance related with the platform design and content, the development and promotion of the 6 concepts for cross-border social enterprises and for ensuring the sustainability and multiplication of the project outcomes by actively engaging the FEMTERPRISE Network members

## Developing a holistic concept (methodology) for organization and conducting the FEMTRERPRISE capacity-building and empowerment training for young women entrepreneurs and to lecturе and moderatе the training sessions in accordance with the developed concept (methodology);

5-day/4 nights FEMTERPRISE training will be organized in the Macedonian border area, gathering 30 potential female entrepreneurs identified by the research (15 BG and 15 MK),5 project team members and the 6 mentors (4 BG and 2 MK). The purpose of the training is to empower young women with entrepreneurial potential by building their entrepreneurial and leadership capacity and to lay the foundations of the FEMTERPRISE Network of Women Entrepreneurs (FNWE).  The training sessions should follow the logic and content of the FEMTERPRISE platform modules. In addition, the FEMTERPRISE competition should be initiated during the training by forming the teams, identifying ideas, distributing tasks, etc.; A session for generating ideas on how to sustain and multiply the FNWE as well as presentation of the draft version of the FEMTERPRISE platform should be presented to the participants for feedback and recommendations.  The Consultant should develop as minimum the following materials for the training: agenda, program-methodological materials/presentations, feedback forms.

The purpose of the training is to strengthen the leadership capacity, to increase management, financial, fundraising and legal knowledge and skills, and to foster entrepreneurial spirit and leadership attitude of participants through informal learning methods and trainings, outdoor and grassroots activities and ongoing mentor support.

The method applied for the trainings should include training sessions on the different topics described above, all designed to advance the socio-professional and entrepreneurial skills of the participants. Training sessions should also emphasize on popularizing the concept of social entrepreneurship and the visibility of entrepreneurs as role models. Through experiential learning participants should master the mind and skill-set necessary for creating successful social enterprises,  become acquainted with existing legal and regulatory base and funding opportunities and should engage in the FEMTERPRISE online competition following the training.

The FEMTERPRISE training is crucial for establishing a sustainable cross-border FEMTERPRISE Network comprising of young female entrepreneurs, mentors and local stakeholders such as investors, businesspersons, policy makers, NGOs, educational institutions and community leaders. The training should be designed in a way ensuring positive, supportive and creative environment and climate for open communication, encouraging project participants to be proactive and “out-of-the-box” thinkers. Apart from the daily training sessions, the Consultant should include in the training programme outdoors and evening team-building activities, for example: hiking trips, sports activities, thematic evenings, etc. In the end of the training, we expect participants to report increased leadership, entrepreneurial and fundraising skills, as well as raised sense of community and supportive peer environment.

### Development of a holistic concept (methodology) for organization and conducting the FEMTERPRISE online competition for development of 6 social enterprise concepts and guiding and moderating the competition in accordance with the developed concept

The FEMTERPRISE Competition will be launched at the FEMTERPRISE training and will continue online through the platform and social media, lasting 3 months. Its purpose is to foster creative and competitive environment for generating 6 FEMTERPRISE concepts for cross-border social enterprises.

At the FEMTERPRISE training, the 30 young female entrepreneurs will be divided into 6 teams comprising of average 5 members (balanced BG/FYROM participation) and 1 mentor each. In order to maximize the mentor expertise, in the online phase of the competition, all mentors will rotate on 2-week basis, thus providing the necessary specialized expertise (legal/business, etc.) to each team. Online promotion campaign will be run in parallel with the competition and contestants will attract supporters of their ideas, thus popularizing the project and the platform among target groups.

The mentors will be responsible for guiding the teams of participants into identifying and developing their holistic concept of a cross-border social enterprise, assigning tasks and regular online “meetings” of the teams in order to discuss, moderate and assess the progress of each team’s idea, motivate participants to be proactive and responsible team players, and, in the end, come up with a holistic concept of a cross-border enterprise which will be presented and assessed by an independent cross-border jury at the FEMTERPRISE workshop following the online contest.

### Development of a holistic concept (methodology) for organization and conducting the FEMTERPRISE networking workshop and facilitation and moderation of the training and workshop sessions in accordance with the developed concept:

### After the conclusion of the online competition the 6 teams and mentors will present their concepts at a 3-day/2 night FEMTERPRISE entrepreneurial & networking workshop, organized in the FYROM border area. Stakeholders, mentors and investors identified through the research will attend the workshop as jury and founding members of the FEMTERPRISE Network. The 30 FEMTERPRISE entrepreneurs, 16 mentors (4 Bulgarian mentor team, 2 Macedonian mentor team and 10 volunteer-mentors), 6 project team, 4 translators, 4 jury members and at least 16 other stakeholders and potential investors will take part in the workshop. The workshop will have the following objectives:

- To present the final version of the FEMTERPRISE Platform and the elaborated during the training and online contest 6 concepts for social enterprises;

- To announce the winner in the online competition - the concepts will be assessed by an independent cross-border jury. The winning concept will be awarded real world development;

- To announce the People’s Choice Award– special award for the concept gathered the most votes of supporters during the online campaign;

- To strengthen the FEMPTERISE Network – by presenting the young entrepreneurs and their ideas to local stakeholders, potential investors, media, etc. and organising networking sessions and evening events.

- To ensure the multiplication and sustainability of the FEMPTERISE Network after the project closure – by designing sustainable and successful exit/continuation strategy.

The developed by the Consultant methodology for organizing and conducting the workshop should be designed in a way ensuring the achievement of the workshop objectives, with special emphasis on design and moderation of productive networking sessions aiming to establish meaningful and long-term relationships between young entrepreneurs, investors and other stakeholders, and viable multiplication and sustainability strategy. The Consultant should develop as minimum the following materials for the training: agenda, session outlines, program-methodological materials/presentations, feedback forms.

### Support of the participants in the real world development of the winning FEMTERPRISE concept for cross-border social enterprise:

### After the jury determines the winning concept from the online contest, the all members of the mentor team with the support of the project management team, should engage in its real-world development. The real world development of the winning FEMTERPRISE concept aims at setting up 1 cross-border social enterprise and should include:

### Identification of social and/or environmental mission and business strategy

### Development of a detailed business plan

### Establishment and legal registration of the enterprise

### Exploring funding options

### Identifying proper funding source and development of application

### Submitting the application by the end of the project in case there is an open call or other appropriate funding opportunity. Otherwise, the proposal should be submitted in accordance with the deadlines stipulated in the identified call for proposals/other funding opportunity.

Throughout the real world development, the teams should work in virtual environment through the FEMTERPRISE platform/social media. They should meet once, as part of the scheduled project team meetings. The project and mentor teams, together with all 30 participants should identify at least 1 funding source for each of the 6 developed concepts.

### Providing professional advice to the remaining 5 teams for further development of their concepts:

The Consultant should support the remaining 5 teams by providing mentor advice for further development of their concepts and facilitating contacts with potential investors (if the case).

### Actively participating in the online promotion campaign by providing professional mentor advice and guidance via the web platform and social media.

## The online campaign will aim to maximize the number of final beneficiaries by popularizing the project’s outcomes and EU contribution.  It will last 6 months and will involve at least 3000 target groups representatives (BG and MK) by using the most popular social media tools, allowing young women from multiple locations to become members of the FEMTERPRISE Network.

## Female entrepreneur’s success stories, the concept of social enterprises and their importance for the social, cultural, economic and environmental development of the communities will be important highlight of the campaign. Successful businesspersons, policy makers and potential investors identified during the research will be invited to join the campaign as volunteer mentors and speakers.

The design, organization and implementation of the online campaign are subject of a different service contract. The Consultant should support the campaign by providing mentor advice and guidance in the FEMTERPRISE social media accounts on legal, business, psychological and financial/fundraising matters related with social entrepreneurship. We expect the Consultant to be actively engaged in the discussions organized throughout the campaign. The Consultant, together with the project participants should use the campaign for promotion and attraction of supporters of the 6 FEMTERPRISE concepts generated and developed during the training and online contest.

### Providing professional consultation to the project management team with regard to eventual upgrade the FEMTERPRISE platform content after the project closure.

### For the two years following the project closure, once a year, the Consultant, in cooperation with the other members of  mentor team, should go through the FEMTERPPRISE platform program-methodological content and if there are outdated elements, for example funding programmes/sources that exist no more, changes in the legal framework, etc. propose upgrades in the form of written recommendations to the project management team.  	 
In the implementation of the abovementioned tasks, the Consultant should work in close cooperation with the project management team, the designers and developers of the online platform and the online marketing team. Despite the fact that the Bulgarian and Macedonian mentor teams will be contracted by different contracting authorities, the Consultant should perceive both teams as one joint cross-border mentor team and therefore work with its Bulgarian colleagues in close collaboration, using virtual team-work environment and attending the scheduled meetings. Furthermore, a representative of the Consultant should attend the multidisciplinary team sessions (meetings between the project management team and the consultants responsible for platform design and development, online campaign organization, etc. Unikum-kos and Viva Pautalia will ensure the venue and all other supporting stuff throughout these meetings.

## Project management

### Responsible body

Unikum-kos

### Management structure

Unikum-kos (LP) will be responsible for the general coordination, management and implementation of the project in Macedoniа and Viva Pautalia will be responsible for the implementation part in Bulgaria. Both partners will implement all designated activities in accordance with the description contained in the Subsidy Contract, Partnership Agreement, approved AF and relevant Programme rules and regulations.

A joint project management team will be established, comprising of 5 experts with different roles:

LP: Project manager (overall management, reporting and control), financial manager (overall financial management, reporting and control, PRAG procedures in Macedonia, technical assistant (organization of events, information and publicity in Macedonia)

PP2: Project coordinator (coordination, reporting and control of PP2 activities, information and publicity BG) procurement expert (PRAG procedures, BG).

The communication and reporting between all actors involved in the project will be implemented through a professional online-based tool for project management. 3 joint meetings will take place.

As far as the Contractor is concerned, all the communication and correspondence with the Contracting authority will be realized with the Project Manager of Unikum-kos Association .

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

Kumanovo, Macedonia

## Start date & Period of implementation of tasks

The intended start date is the date of signing the contract and the period of implementation of the contract will be 11 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key expert 1: Jurist

Qualifications and skills

- University degree in Law or equivalent;

- Excellent command of English Language;

- Profound knowledge in Commercial law

Key expert 2: Business Mentor

Qualifications and skills

- University degree in Law, Economics, Finance, Business management, Business development, Business administration or equivalent

- Excellent command of English Language;

- Sound knowledge of entrepreneurship with emphasis on social entrepreneurship

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

N/A

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

## The Contractor shall ensure that experts are adequately supported and equipped. In particular it must transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original:

- Inception Report of maximum 12 pages to be produced after 10 days from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should proceed with his/her work unless the Contracting Authority sends comments on the inception report.

- Interim Report(s) including the following: Developed program - methodological content of the FEMTERPRISE platform and “Create your own business model” tool; Developed program - methodological content of the Social Entrepreneurship Practical Guide; Developed holistic concept (methodology) for organization and conducting of the FEMTERPRISE  training, workshop and online contest– programme, scenario, training modules, tasks for the teams, feedback forms etc. The reports should be submitted in accordance with previously agreed time schedule with the contracting authority.

- Draft final report of maximum 20 pages (main text, excluding annexes). This report shall present the results of all the completed tasks during the implementation of the contract. The draft final report should be submitted no later than one month after the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 10 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision. The report should be done in compliance with the requirements of the Tor stated above. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Coordinator identified in the contract. The Project Coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

## Developed program-methodological content of the FEMTERPRISE platform;

## Developed program-methodological content for Social Entrepreneurship Practical Guide;

## Developed holistic concept (methodology) for organization and conduction of training, workshop and contest– programme, scenario, training modules, tasks for the teams, etc.;

## Real world development of the winning concept;

## Ongoing mentor support and advice.

## Special requirements

A draft version of every major element of the platform content, Guide content or concept for organization of the training, workshop and online contest which is about to be elaborated has to be preliminary presented to the representative of the Contracting authority for approval. Only after receiving such an approval the contractor could proceed to elaborating the product in its final version.